## Summary
EVO Main Uint EE test plan and report
| Last updated: | 2023-11-22
| Revision | 1
General summary
1 | PROGRAM INFO
| Project Name | EVO
| Development Phase | DVT
3 | BOARD ASSEMBLIES
Main PCB
Battery pack
Lamp
4 | ISSUES
| Open without fix/solution | no charger test point
Open with fix/solution
Total
5 | PCB & PCBA
| Item | Part Number | Description
| Main Board |  | Evo main uint PCB board PlanB Rev1
| Battery pack | C00281-103-EL-IFR26650G2W-3S2P | LiFePO4 9.6V 6700mAh bfrom BST Battery
Lamp
Wireless module
Revision History
# | Revision | Date | Description | Owner
1 | EVT | 2023-11-18 | initial draft | Nan Liu

## Test Plan
EVO Test Plan and Report | [9 empty] | 23 | 4 | total test
Last updated | 2023-12-01 | [8 empty] | 15 | 0 | total completed
[10 empty] | 0 | 0 | total fail
[10 empty] | 0 | 0 | total WIP
[10 empty] | 0 | 4 | total TO DO 1
[10 empty] | 0 | 0 | total TO DO 2
[10 empty] | 0 | 0 | N.A.
check prerequisite for FW dependencies on special commands
# | DESCRIPTIONS | TEST OBJECTIVES & DESCRIPTION | TEST PROCEDURE | EVALUATION / MEASURED OUTPUT | PREREQUISITE | SPECS IDENTIFUER REF No. | Owner | Reviewer | TEST JIG RESULTS | DVT | MVT RESULTS | REMARKS
1 | PCB Appearance and Assembly Inspection | [8 empty] | PASS
1.1 | MLB | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Shaun | Chin Wee | N.A. | PASS
1.2 | UI (ICON/FT) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Shaun | Chin Wee | N.A. | PASS
1.3 | Feed Button | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS |  | Removed in UI new ID
1.4 | LSS UPPER | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS
1.5 | LSS BOTTOM | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS
1.6 | RFID Board | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS
1.7 | Wireless board (WIFI/BT) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS
1.8 | Front USB (Cable Assembly) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS |  | Re-used PM43
1.9 | Rewinder Board (Re-used Qilin) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee | N.A. | PASS | TO DO 1 | Venture first time doing production for Qilin boards
1.10 | Applicator Board (Re-used Qilin) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee |  | PASS | TO DO 1 | Venture first time doing production for Qilin boards
1.11 | Industrial Board (Re-used Qilin) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee |  | PASS | TO DO 1 | Venture first time doing production for Qilin boards
1.12 | Parallel Boad (Re-used Qilin) | Visual inspection on the board quality, soldering quality and component assembly. | visual inspection | no visual defect on the board | NA |  | Rizam | Chin Wee |  | PASS | TO DO 1 | Venture first time doing production for Qilin boards
2 | Board Level
2.1 | Power Supply
2.1.1 | AC Iutput voltage | Validate the Fly-back circuit through AC supply voltage range. | 1. probe votage rail and measure rise time and sequence | power up as per IC datasheet | oscilloscope |  | Nan |  | N.A. | PASS
2.1.2 | 14V DC output voltage | Validate the Fly-back circuit DC output through AC supply voltage range. | 1. send a long feed command (ff 24000) 2. probe and measure the various power rail (min, max, noise level) during feeding | power rail value are within the specification (min/max voltage) | oscilloscope |  | Nan |  | N.A. | NA
2.1.3 | 3.3V DC output voltage | Validate the 3.3V DC output through the AC supply range | 1. Connect MLB to printer prototype 2. Connect voltage output to active load 3. Load voltage rail to passing criteria loading condition | current measured to be withing the specification | oscilloscope + current probe |  | Nan |  | N.A. | NA
2.14 | Power Consumption
2.14.1 | System Power Consumption | Validate the system power consumption | 1. Connect System to Variable AC Supply and AC Power Meter 2. Take reading for Sleep Mode (Power Switch off) 3. Take Reading for Full System before went into Energy Saving Mode 4. Take Reading for Full System after system went into Energy Saving Mode | power consumption to be lower than energy star requirement | power meter variable AC supply FW ready to enable idle mode |  |  |  | N.A. | NA
2.14.2 | Charger Power cimsumption | Evaluate the power consumption at low power mode Determine which modules to be turned off at low power mode Quantify the margin | 1. Connect System to Variable AC Supply and AC Power Meter 2. Take reading for Sleep Mode (Power Switch off) 3. Take Reading for Full System before went into Energy Saving Mode 4. Take Reading for Full System after system went into Energy Saving Mode | power consumption to be lower than energy star requirement | power meter variable AC supply FW ready to enable idle mode |  |  |  | N.A. | NA
2.14.3 | Lamp Power Consumption | Evaluate the state and power consumption at low power mode Quantify the margin | 1. Connect System to Variable AC Supply and AC Power Meter 2. Take reading for Sleep Mode (Power Switch off) 3. Take Reading for Full System before went into Energy Saving Mode 4. Take Reading for Full System after system went into Energy Saving Mode | power consumption to be lower than energy star requirement | power meter variable AC supply FW ready to enable idle mode |  |  |  | N.A. | NA
2.15 | Temperature
2.15.1 | Operating Temperature | Measure and validate the system performance within the specified temperature ragne | 1. add thermal probe on critical IC (MLB + PSU) 2. place printer in chamber at 45C 3. run continuously and monitor temperature | no over heating of critical IC no error message Temperature of enclosure at printhead | chamber datalogger thermal probe + thermal glue |  |  |  | N.A. | PASS |  | Conducted by Reliability team
3 | Functional Test
3.1 | Brownout | Validate the brownout function to meet the UL requirements | 1. use variable AC power to set voltage at 90V, 100V, 240V, 264V 2. Probe 24V and 33V | line regulation to be +/-1% load regulation to be +/-3% | variable AC power power meter scope |  |  |  | N.A. | NA
3.2 | Charge the battery | Validate the battery charge cuurent and charge time | 1. increase load / voltage until failure | find out - check with Harry / Han Tiong | find out - check with Harry / Han Tiong |  |  |  | N.A. | NA
3.3 | Manual Test and auto-Test | Validate the manual and scheduled test functions and error code/indications | 1. add thermal probe on critical IC (MLB + PSU) 2. place printer in chamber at 45C 3. run continuously and monitor temperature | no over heating of critical IC no error message | chamber datalogger thermal probe + thermal glue |  |  |  | N.A. | NA
3.4 | Heater | Validate the the heating function and heater performance | 1. add thermal probe on critical IC (MLB + PSU) 2. place printer in chamber at 45C 3. run continuously and monitor temperature | no over heating of critical IC no error message | chamber datalogger thermal probe + thermal glue |  |  |  | N.A. | NA
4 | EMC/EMI Test
Note
PASS | Test Pass
PASS after rework | Test Pass after doing rework
FAIL with solution | Test Fail with solution (not validated)
FAIL | Test Fail with no solution
N.A. | Not applicable
Info | For Information only
WIP | Work in Progress
Total no of test | TO DO 1: must do in first priority TO DO 2: secondary set of test, to be done after TODO1 test TO DO 3: third set of test to complete. Can be postpone on next board test
Total no of units
Total Duration
Resource
Key Prerequisite
1 | 1 UI alert/error message ready in FW
2 | 2 conversion table from Temp to ADC
3 | 3 CPU register reading
4 | 4 Current probe: Tektronix TCP A300
5 | 5 dataloger
6 | 6 datasheet from DST
7 | 7 DC Electronic load: BK Precision 8500
8 | 8 DDR read/write tool
9 | 9 ESD simulator
10 | 10 extreme case media (worst/best case)
11 | 11 FPGA register reading - memtool
12 | 12 functest command available
13 | 13 FW enable read/write to LPH
14 | 14 FW low power / idle mode enable
15 | 15 input self check wizard ready (by FW)
16 | 16 microphone
17 | 17 oscilloscope
18 | 18 Oscilloscope: Agilent MSO6104A + in app USB test suite
19 | 19 placement - on final product
20 | 20 power meter
21 | 21 Power supply: CWT GTS-100W
22 | 22 PSU dynamic/static load (check if we have this type)
23 | 23 temp chamber
24 | 24 test strip with opacity variation (to manufacture)
25 | 25 test strip with reflection variation (to manufacture)
26 | 26 thermal probe + thermal glue
27 | 27 UI / webpage
28 | 28 variable AC power
29
30
31
32
33

## 2. Board Level
2 | Boaed Level Tests
>> back to EE test plan
A. OBJECTIVES
Motor - step, clock and control signal integrity test.
Evaluate motor control performance
Core control IC DRV8452
B. RESULT SUMMARY
Item | Spec. |  |  | Result |  |  |  | Remark
AC Input Voltage (Test 1) | fSTEP | max 500KHz |  | PASS
| tWH_STEP | min 970ns |  | PASS
| tWL_STEP | 970ns |  | PASS
RWD_DIR (Test 2) | tH_DIR | min 200ns |  | N/A
| tSU_DIR | min 200ns |  | PASS
RWD_MS1/MS2 (Test 3) | tH_M1 | min 200ns |  | N/A
| tH_M2 | min 200ns |  | N/A
| tSU_M1 | min 200ns |  | PASS
| tSU_M2 | min 200ns |  | PASS
C. TEST SETUP
1. PM45 MLB: 50172011-006 revision
2. Probe Motor control signals
3. Telnet to printer ip address using port 23, root access
4. send functest FORMFEED 1000
5. Observe the waveforms
D. TEST DETAILS
1. Test 1
AC test:
|  | Standby mode |  | CC charge mode |  | Float charge mode |  | Heating mode
| AC Input(V) | Current(mA) | Power Draw (W) | Current(mA) | Power Draw(W) | Current(mA) | Power Draw(W) | Current(mA) | Power Draw(W)
| 310 | 7.01 | 0.84 | 134.4 | 16.51 | 64.8 | 7.56 | 205.9 | 26.05
| 277 | 6.6 | 0.68 | 144.7 | 17.28 | 70.3 | 7.42 | 222.4 | 25.89
| 220 | 6.11 | 0.25 | 179.2 | 16.72 | 82.3 | 7.19 | 261 | 25.91
| 120 | 7.03 | 0.26 | 266.9 | 17.18 | 125.5 | 6.98 | 412 | 25.61
2. Test 2
DC test:
|  | Standby mode |  | CC charge mode |  | Heating mode
| AC Input(V) | 14V DC output(V) | 3.3V DC Output(V) | 14V DC outputV) | 3.3V DC Output(V) | 14V DC Output(V) | Heater Current (mA) | Heater Power Draw(W)
| 310 | 14.31 | 3.32 | 14.19 | 3.32 | 13.816 | 1641 | 22.6721
| 277 | 14.31 | 3.32 | 14.19 | 3.32 | 13.811 | 1616 | 23.125
| 220 | 14.3 | 3.32 | 14.27 | 3.32 | 13.8 | 1613 | 23.0659
| 120 | 14.3 | 3.32 | 14.3 | 3.32 | 13.8 | 1608 | 22.9944
[9 empty] | Shunt Resister Volt(mV) | Current(mA) | Power_Max(W)
[9 empty] | 93 | 1367.6471 | 14.9757
4. Test 4
5. Test 5
6. Test 6
[12 empty] | tWAKE | 2.14ms
[12 empty] | tWAKE | 2.14ms

## 3. Functional Test
3 | Functional Test
>> back to EE test plan
A. OBJECTIVES
Evaluate the functions performing correctly
B. RESULT SUMMARY
Item | Spec | Speed | V33V_S (RMS) | Result | Remark
Test 1 | No significant dip in motor voltage | 2ips | 32.85 | Pass
|  | 4ips | 32.88 | Pass
|  | 6ips | 32.84 | Pass
|  | 8ips | 32.84 | Pass
|  | 10ips | 32.83 | Pass
|  | 12ips | 32.87 | Pass
|  | 14ips | 32.87 | Pass
C. TEST SETUP
1. PM45 MLB: 50172011-006
2. Probe signals: RWD_RESET_N, RWD_STEP and 33V_S
3. Telnet to printer ip address using port 9100
4. send functest FORMFEED 5000
5. Record the waveforms
D. TEST DETAILS
1. Test 1

## 4. EMC EMI Test
4.8.2 |  | Radiated Emission
>> back to EE test plan | [7 empty] | Done By: | Heng Chiang Yong, 14 May 2021
A. OBJECTIVES
Pass Radiated Emission (Class B)
B. RESULT SUMMARY
Date | Test Case (Sheet) | Unit |  | Sandby Mode | Brownout Mode | Test Mode | Results | Result location
xx/xx/2024 | 1 | EVO Rev_X | 1st DVT unit |  | - | -
xx/xx/2024 | 2 | EVO Rev_X | 2ndDVT unit |  | - | -
xx/xx/2024 | 3 | EVO Rev_X | 3rd DVT unit |  | -
C. TEST SETUP
Setup in UL
D. TEST DETAILS
1. Test 1
Refer to UL RE scan results in location listed in B. Results Summary table
E. SPECIFICATIONS
Note on H21: Lee, Chin Wee: 500MHz 0.5dB : likely due to external cable routing
Note on H22: Lee, Chin Wee: 144MHz failed by 0.3dB (likely cause is due to cable routings/grounding after rework to swap UI board in UL)
Note on H26: Lee, Chin Wee: Pass with small margin
Note on H29: Lee, Chin Wee: Pass with small margin
Note on H31: Lee, Chin Wee: Remove insulation tape (same setup as sheet 1 of EMC-21-0144_Intermec(Honeywell)_13082021.xlsx results)